## Planned_vs_Actual_Sprint
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Setup & Database Configuration | MUST HAVE | No Dependency | Intern | Completed
S1 | S1 | US-002 | Inventory Data Modeling & Schema Design | MUST HAVE | US-001 | Intern | Completed
S2 | S2 | US-003 | Product & Category Management Module | MUST HAVE | US-002 | Intern | Completed
S2 | S2 | US-004 | Stock Management & Update Logic | MUST HAVE | US-003 | Intern | Completed
S3 | S3 | US-005 | Supplier & Purchase Order Module | MUST HAVE | US-004 | Intern | Completed
S3 | S3 | US-006 | Inventory Tracking & Reporting Dashboard | MUST HAVE | US-005 | Intern | Completed
S4 | S4 | US-007 | Role-Based Access & Security Implementation | MUST HAVE | US-006 | Intern | Completed
S4 | S4 | US-008 | System Testing & Deployment | MUST HAVE | US-007 | Intern | Completed

## Sprint_1_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours
US-001 | 1 | Spring Boot Setup & DB Configuration | 04-Feb-2026 | 17-Feb-2026 | Intern | 3-Completed | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0
US-002 | 2 | Inventory Schema Design | 04-Feb-2026 | 17-Feb-2026 | Intern | 3-Completed | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0

## Sprint_2_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours
US-003 | 1 | Product & Category CRUD Module | 18-Feb-2026 | 04-Mar-2026 | Intern | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
US-004 | 2 | Stock Update & Validation Logic | 18-Feb-2026 | 04-Mar-2026 | Intern | 3-Completed | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0

## Sprint_3_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours
US-005 | 1 | Supplier & Purchase Order Management | 05-Mar-2026 | 18-Mar-2026 | Intern | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0
US-006 | 2 | Inventory Dashboard & Reports | 05-Mar-2026 | 18-Mar-2026 | Intern | 3-Completed | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0

## Sprint_4_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity Status | Original Estimate Effort (In Hours) | Day 1 Pending Hours | Day 2 Pending Hours | Day 3 Pending Hours | Day 4 Pending Hours | Day 5 Pending Hours | Day 6 Pending Hours | Day 7 Pending Hours | Day 8 Pending Hours | Day 9 Pending Hours | Day 10 Pending Hours
US-007 | 1 | RBAC & Security Implementation | 19-Mar-2026 | 01-Apr-2026 | Intern | 3-Completed | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
US-008 | 2 | Testing, Bug Fixing & Deployment | 19-Mar-2026 | 01-Apr-2026 | Intern | 3-Completed | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0